## Sheet1
Phase ID | Phase Name | Phase Type | Phase Status | Phase Order | Duration | Dependencies | Deliverables | Activities | Resources | Tools | Milestones | Risks | Success Criteria | Start Date | End Date | Completion | Notes | Tags
PHASE-001 | Requirements Analysis | Analysis | Completed | 1 | 2 weeks | Project Initiation | Requirements Document, Use Cases | Stakeholder interviews, Requirements gathering | Business Analyst, Product Owner | Confluence, Jira, Visio | Requirements Sign-off | Scope creep, Changing requirements | All requirements documented and approved | 2024-01-01 | 2024-01-14 | 100 | Requirements phase completed ahead of schedule | requirements,analysis,stakeholders
PHASE-002 | System Architecture Design | Design | In Progress | 2 | 3 weeks | Requirements Analysis | Architecture Diagrams, Technical Specifications | System design, Technology selection | Solution Architect, Technical Lead | Draw.io, Lucidchart, Architecture Tools | Architecture Review | Technology constraints, Performance issues | Architecture meets performance and scalability needs | 2024-01-15 | 2024-02-04 | 75 | Architecture review scheduled for next week | architecture,system,technical
PHASE-003 | Database Design | Design | Completed | 3 | 2 weeks | System Architecture Design | Database Schema, ER Diagrams | Schema design, Performance optimization | Database Administrator, Backend Developer | MySQL Workbench, pgAdmin | Database Approval | Data migration challenges | Database supports all use cases efficiently | 2024-02-01 | 2024-02-14 | 100 | Database design approved by DBA team | database,schema,performance
PHASE-004 | API Design | Design | In Progress | 4 | 2 weeks | System Architecture Design | API Documentation, Swagger Specs | Endpoint design, Authentication setup | API Developer, Integration Specialist | Postman, Swagger Editor | API Review | Integration complexity | APIs are secure and well-documented | 2024-02-15 | 2024-02-28 | 50 | API documentation in progress | api,integration,documentation
PHASE-005 | UI/UX Design | Design | Not Started | 5 | 3 weeks | API Design | Wireframes, Mockups, Style Guide | User research, Prototyping | UX Designer, UI Developer | Figma, Sketch, Adobe XD | Design Approval | User acceptance issues | Designs meet user needs and brand guidelines | 2024-03-01 | 2024-03-21 | 0 | Waiting for design system approval | ui,ux,design,prototyping
PHASE-006 | Testing & Validation | Testing | Not Started | 6 | 2 weeks | UI/UX Design, API Design | Test Plans, Test Cases, Validation Reports | Test execution, Bug tracking | QA Engineer, Test Manager | Selenium, TestRail, Bugzilla | Test Completion | Test coverage gaps | All tests pass, zero critical bugs | 2024-03-15 | 2024-03-28 | 0 | Test environment setup in progress | testing,validation,quality